## Sheet1
WP | Origin | Action point | Date due | Status | Responsible | Comments
5.2 | Athens | To provide real world queries by users and evaluate them: list of queries + scenarios, list of requirements to the API | 2006-05-20 | Delayed | CWI, INA | Missing translation
4.5 | Athens | Integration of the QMUL RF system | 2006-09-30 | Ongoing | QMUL, CWI, DCU, GU
4.5 | Athens | Provide feedback on the performance of the QMUL RF system | 2006-10-15 | Pending | ALL
5.1 | Graz | Provide outline, decide on whether to include NewsML work in D5.1 | 2006-10-15 | Ongoing | CWI
4.1 | Graz | Provide chapters for D4.1 - Image Annotation Tool: 1. Introduction [KU, ITI, CWI], 2. Requirements for an Image Annotation Tool [ITI, KU, CWI, UEP, DFKI], 3. Review of existing Image Annotation Tools [UEP, ITI, KU, CWI], 7.2 Future Work on Video Annotation Tool [CWI, JRS, UEP] | 2006-11-15 | Pending | ITI, KU, CWI, UEP, DFKI, JRS
4.1 | Graz | Provide chapters for D4.1 - Multimedia Ontology Infrastructure: 1. Introduction [KU, CWI], 2. Requirements on a Multimedia Ontology [KU, CWI], 3. Review of existing Multimedia Ontologies [KU, CWI, UEP, ITI, DFKI], 5. Proposal for a Core Multimedia Ontology [KU, CWI, UEP], 6.1 Architecture Overview [KU, UEP, CWI], 6.3 Linkage with Domain Ontologies [UEP, DFKI, KU, CWI], 7.2 Adoption of the Media Format Descriptor [KU, CWI, UEP] | 2006-11-15 | Pending | KU, CWI, UEP, ITI, DFKI
4.1 | Graz | Describe the architecture of the tools and their functionalities (part of D4.1) | 2006-11-15 | Pending | KU, ITI, JRS, CWI
5.3 | Graz | Provide the chapters for D5.3 | 2006-11-15 | Pending | ALL
4.5 | Graz | Initial contribution for D4.5 send to Krishna | 2006-11-15 | Pending | QMUL, DCU, CWI, GET, GU
5.3 | Graz | Provide a complete draft of D5.3 | 2006-11-30 | Pending | CWI
7 | Graz | Draft of next newsletter | 2006-11-30 | Pending | UEP, ALL
8 | Graz | report comments on D8.3 back to DCU | 2006-12-11 | Pending | ALL
5.3 | Athens | Report specification of Semantic Retrieval | 2006-12-31 | Pending | CWI, QMUL
4.1 | Athens | specify ontology modules (to choose one of the ontologies) | 2006-12-31 | Ongoing | ITI, CWI, JRS
5.3 | Athens | First implementation and evaluation of Semantic Retrieval | 2006-12-31 | Pending | CWI, QMUL
3 | Graz | Whenever MPEG-7 metadata exchange is required by any collaboration within KS update MPEG-7 description requirements document on document store and notify JRS for specification | Ongoing | Ongoing | ALL
2 | Graz | report all exchanges to GU – not just PhD exchanges | Ongoing | Ongoing | ALL
7 | Graz | Add public deliverables to the webpage | Ongoing | Ongoing | QMUL, ALL
7 | Graz | Add publications, together with (a link to) the paper | Ongoing | Ongoing | ALL
7 | Graz | Update regularly news sections (including conferences etc) and list of publications. Send to Krishna at QMUL. | Ongoing | Ongoing | ALL

## Sheet2
WP | Origin | Completed Action point | Date due | Status | Responsible | Comments
4.5 | Graz | Email to Krishna for specification of the Query Expansion module in WP4.5 | 2006-09-15 | Done | CWI
5.3 | Graz | Distribute the TOC of D5.3 | 2006-09-22 | Done | CWI | Done on 27/9
5.3 | Graz | Comment and agree on the TOC of D5.3 | 2006-09-29 | Done | ALL
7 | Graz | TOC of next newsletter | 2006-09-30 | Done | UEP, ALL
5.3 | Graz | finalize TOC of D5.3 | 2006-09-30 | Done | CWI
4.1 | Athens | Multimedia Ontology - Module 4: multimedia descriptors: implementation of the ontology | 2006-09-30 | Done | CWI, KU | Work with Simon+Richard.
4.1 | Athens | Multimedia Ontology - Module 5: structure: implementation of the ontology | 2006-09-30 | Done | KU, JRS, CWI, ITI | Work with Simon+Richard
3 | Graz | Send planned contributions / feedback/ideas on MPEG7 infrastructure requirements document to JRS | 2006-09-30 | Done | TUB, GU, GET, INA, EURECOM, EPFL, ITI, KU, CWI
4 | Graz | Gather resources in the repository. This will include collection of tools which do not have already their own official web-page and which are ready | 2006-10-02 | Done | DCU, ALL | Upload IWA to repository
7 | Graz | Design the front page of the SMaRT cluster web site | 2006-10-08 | Done | CWI | Alia
5.2 | Graz | Provide specifications for components of the metadata store | 2006-10-15 | Pending | ALL | Considered as done, since Simon (KU) provided an architecture that was accepted by all partners
5.2 | Graz | Provide chapters for D5.2 - Metadata Store Specification: Evaluation of Existing RDF Stores | 2006-10-15 | Done | CWI
7 | Graz | Offline discussion on the brochure. | 2006-10-31 | Done | UEP, ALL
7 | Graz | bring and present a K-Space Poster at ISWC | 2006-11-06 | Done | CWI