Title	: Discussion of WP 2

Date & Time	: 2006-01-12, 09:00

Date Approved	:

Location	: Queen Mary, University of London

Document	: ks-013-02-qmul-2006-01-12-wp2.doc

Chair	: Alan Smeaton

Author(s)	: Tomas Piatrik

Affiliation(s)	: QMUL

Attendees

| Name | Email | Affiliation |
| --- | --- | --- |
| Keith van Rijsbergen | keith@dcs.gla.ac.uk | GU |
| Alan Smeaton | asmeaton@computing.dcu.ie | DCU |
| Jean Carrive | jean@ina.fr | INA |
| Jan Nemrava | nemrava@vse.cz | UEP |
| Lynda Hardman | Lynda.Hardman@cwi.nl | CWI |
| Vassilis Tzouvaras | tzouvaras@image.ntua.gr | NTUA-ITI |
| Tomas Piatrik | Tomas.Piatrik@elec.qmul.ac.uk | QMUL |
| Wiryadi | wiryadi@nue.tu-berlin.de | TUB |
| Amjad Samour | samour@nue.tu-berlin.de | TUB |
| Lutz Goldmann | goldmann@nue.tu-berlin.de | TUB |
| Herwig Rehatschek | herwig.rehatschek@joanneum.at | JRS |
| Touradj Ebrahimi | touradj.ebrahimi@epfl.ch | EPFL |
| Thierry Declerck | declerck@dfki.de | DFKI |
| Gaël Richard | gael.richard@enst.fr | GET.ENST |
| Craig Stewart | craig.stewart@elec.qmul.ac.uk | QMUL |

1.0 Introduction and meeting objectives

Meeting started at 9:00. The welcome and approval of agenda was presented by DCU (Alan Smeaton, acting in place of GU, whose attendee sent his apologies but would be arriving later). The group discussed about K-Space interaction activities and progresses.

The K-Space interaction activities and progresses in WP2 can be summarized as below.

1.1. Various Activities in the work plan to ensure true integration in K-Space occurs

- Exchange of academic researchers and PhD students (dedicated fund to support this) GU;

- Industrial placement of research personnel (industrial advisory board is invaluable here) UEP;

- Shared Teaching resources (initially lecture and course materials) TUB;

- Summer Schools and European Masters programs GET

2.0 WP2.1 Exchange of academic researchers and PhD students

The initial collaboration was initiated between GU, UEP and QMUL. Partners discussed about upper limit for a PhD exchange grant and advertising documents. The upper limit for a PhD grant was advised to be approximately €5,000, but this will depend upon circumstances. Grants for the exchange of academic researchers will be paid from the partners own budgets, as arranged between the guest’s home institution and the host’s.

To enable the project to achieve the goal of 15 exchanges in the first 18 months all partners need to advertise this exchange program, to do this advertising materials need to be created.

Action Point 1 (QMUL): will collect advertising data from partners and produce and advertising document. Date: 2006-02-20

Action Point 2 (QMUL, GU): will complete documentation and pass this onto partners. Date: 2006-01-27

3.0 WP2.2 Industrial placement of research personnel

EPFL: It is uncertain who pays for the placement?

EPFL have 2 possible placements in place. This placement scheme will also need to be advertised within the Network. The partners agreed to create advertising materials.

Action Point 3 (QMUL): To will collect advertising data from partners and produce and advertising document. Date: 2006-03-20

4.0 WP2.3 Shared Teaching Resources

Action Point 4 (TUB): to gather a list of teaching resources from all partners and use this to create a resource framework. The draft of this will be available at the next WP2 meeting in M3. Date: 2006-03-20

5.0 WP2.4 Summer schools and European Master and PhD program

The task is led by GET. Locations for 2006 / 2007, along with the organisation of the Summer Schools were agreed. A summer school is planed for each year during July or August. The summer school 2006 will be organized by the Activity leader GET and it is a main milestone.

Action Point 5 (GET): Will contact Paola Hobson (Motorola) to investigate if the 2006 summer school will be held jointly with aceMedia. Date: 2006-01-27

GU: The 2007 summer school will be run by GU.

The European Master and PhD program is planed in several phases. This represents the first phase towards the harmonization of high level education in Europe. This is a long term goal and will initially involve only a few partners.

The first phase of the Master program will be planned for September 2006, in which there will be sharing of materials across institutions but each will teach its own students locally from those common materials.

Action Point 6 (QMUL): QMUL will examine previous European MSc frameworks, e.g. KnowledgeWeb and other bodies such as Erasmus Mundus. Date: 2006-03-20

First phase for a proposition of a European Ph.D. Program:

In this first phase, different initiatives will be promoted including: the establishment of a co-supervision framework, the introduction of special distinctions such as the European Doctorate distinction for Ph.D. thesis defended in front of a truly international board of experts. Ultimately, these actions will lead to a much stronger integration of doctoral programs between the universities of the network.

Action Point 7 (GU, GET): the legal ramifications of having a jointly supervised PhD across multiple European institutions need to be investigated. GU & GET agreed to investigate a co-supervision between them. Date: 2006-03-20

6.0 Progress and summary

- Researcher exchange - infrastructure for documenting is in place, guidelines, and etc. done, preparing “advertising” materials.

- Similar advertising materials to be used for industry placements.

- Have agreed mechanisms to poll partners for available teaching materials and a schedule to gather, categorize and integrate them for internal and restricted external access.

7.0 Summary of Action Points

| Action | Partners Responsible | Description | Dates | Status |
| --- | --- | --- | --- | --- |
| 1 | QMUL | To this end QMUL will collect advertising data from partners and produce and advertising document | 2006-02-20 |  |
| 2 | QMUL and GU | QMUL will complete documentation and pass this onto partners | 2006-01-27 |  |
| 3 | QMUL | To this end QMUL will collect advertising data from partners and produce and advertising document | 2006-03-20 |  |
| 4 | TUB | To gather a list of teaching resources from all partners and use this to create a resource framework. The draft of this will be available at the next WP2 meeting | 2006-03-20 |  |
| 5 | GET | Will contact Paola Hobson to investigate if the 2006 summer school will be held jointly with aceMedia. | 2006-01-27 |  |
| 6 | QMUL | Will examine previous European MSc frameworks, e.g. KnowledgeWeb and other bodies such as Erasmus Mundus | 2006-03-20 |  |
| 7 | GU and GET | The legal ramifications of having a jointly supervised PhD across multiple European institutions need to be investigated. GU & GET agreed to investigate a co-supervision between them | 2006-03-20 |  |