## Sheet1
Action | Responsible | Description | Date | Status
AP.4.8.1 | EURECOM, ALL | Partners have to complete the indicators for D8.1 | 2006-10-31
AP 4.2.1 | ALL | report all exchanges to GU – not just PhD exchanges | Ongoing
AP 4.2.2 | QMUL | to set up a webpage reflecting the status of the exchanges. Basis will be the Excel sheet, amended by the intended exchanges mentioned above | 2006-09-15
AP 4.2.3 | ALL | all partners submit potential candidates to QMUL; skills and references to be described in more detail! Pool will be based on the PhD exchange details | 2006-09-30
AP 4.2.4 | ALL | from September onwards / partners to contact actively spin-off and partner companies with the existing list | 2006-09-30
AP 4.2.5 | TUB | provide an information document on shared teaching resources (list of contacts, objectives) | 2006-09-30
AP 4.2.6 | TUB | open up website for accessing resources | 2006-10-30
AP 4.2.7 | GU, EURECOM | provide details of the intended teaching resource submissions to TUB | 2006-09-30
AP 4.2.8 | GET | identify responsible persons from each university partner | 2006-09-15
AP 4.2.9 | GET | define a list of modules based on pre-existing master programs related to K-Space | 2006-09-15
AP 4.2.10 | GET | inform participants about the meeting or lack of it | 2006-10-30
Action | Partner Responsible | Description | Date | Status
AP4.7.1 | QMUL | Add some internal deliverables to the web page | 2006-09-30
AP4.7.2 | QMUL | Add PR material | 2006-09-30
AP4.7.3 | QMUL | Action on the participation of K-Space Webpage to the IST Award for best web pages. | 2006-09-30
AP4.7.4 | QMUL | Add to the bi-monthly report a mandatory field for news for every partners | 2006-09-10
AP4.7.5 | QMUL | Add a link to SmaRT cluster web page | 2006-09-30
AP4.7.6 | QMUL | Add the W3C logo | 2006-09-30
AP4.7.7 | QMUL, ALL | Add public deliverables to the webpage | 2006-08-31
Ongoing
AP4.7.8 | QMUL, ALL | Add publications, together with (a link to) the paper | 2006-08-31
Ongoing
AP4.7.9 | ALL | Update regularly news sections (including conferences etc) and list of publications. Send to Krishna at QMUL. | 2006-08-31
Ongoing
AP4.7.10 | DCU | Send to QMUL (links to) downloadable show cases demonstrators (DCU)
When tools are available
AP4.7.11 | TUB | Link the web page to WP2 teaching resources, once the license issues have been solved | No fixed date
AP4.7.12 | CWI | CWI offers to create the SmaRT webpage | 2006-10-08
AP4.7.13 | UEP, ALL | Offline discussion on the brochure. | 2006-10-31
AP4.7.14 | UEP, ALL | TOC of next newsletter | 2006-09-30
AP4.7.15 | UEP, ALL | Draft of next newsletter | 2006-11-31
AP4.7.16 | DFKI | To provide for an updated document on the Scientific Forum, which will be the base for the final choice of the legal form of the Scientific Forum | 2006-10-31
AP4.7.17 | EPFL, ALL | Generate a candidate TOC of the (first) book. End of September | 2006-09-30
AP4.7.18 | ALL, EPFL | Contact MPEG (EPFL?) to manage a liaison activity on the semantic multimedia | 2006-09-30
AP4.7.19 | CERTH, ALL | Finalize the list representative of each partner of K-Space for W3C | 2006-09-30
AP4.7.20 | ALL, GET, DFKI | Provide for new technology transfer items to GET (ALL) | Ongoing
AP4.7.21 | ALL | DFKI and GET to provide for an example of a past submission (End of October) | 2006-10-31
Nr. | Responsible | Description | Date | Status
AP4.6.1 | GU | Fill questionnaires on planned contribution | 2006-09-30
AP4.6.2 | EURECOM | Finalize the status on the existing tools and planned tools and to report to DCU | 2006-09-30
AP4.6.3 | DCU | Distribute the plan for gathering of all resources which are ready to be contributed | 2006-09-08
AP4.6.4 | DCU, ALL | Gather resources in the repository. This will include collection of tools which do not have already their own official web-page and which are ready | 2006-10-02
AP4.6.5 | QMUL, DCU, TUB | Propose/discuss the plan for making the access to the three SVN repositories transparent | 2006-09-15
AP4.6.6 | QMUL, DCU, TUB | Implementation of the single access point to all three SVN repositories and a common framework for login | 2006-09-30
Action Point | Responsible | Description | Date | Status
AP 4.5.1 | JRS, ITI, KU | decide which datatypes to support | 2006-12-15
AP 4.5.2 | ITI, KU | to describe how FuzzyOWL can be stored in existing RDF repositories | 2006-09-30
AP 4.5.3 | CWI | To provide outline and to decide on whether to include chapter 4 in D5.1 | 006-10-15
AP 4.5.4 | KU | Create architecture draft | 2006-09-01 | done
AP 4.5.5 | All | Provide specifications for components of the metadata store | 2006-10-15
AP 4.5.6 | KU | deliver D5.2 | 2006-10-31
AP 4.5.7 | CWI | finalize TOC of D5.3 | 2006-09-30
AP 4.5.8 | ALL | D5.3 provide chapters | 2006-11-15
AP 4.5.9 | CWI | first complete draft of D5.3 | 2006-11-30
AP 4.5.10 | QMUL, KU, JRS, ITI | Suggest contribution to task 5.4 | 2006-09-30
AP 4.5.11 | DFKI, UEP; DCU, GU | First experiments in text-video mapping in the football domain | 2006-10-30
AP 4.5.12 | UEP | Partial draft of D5.4 | 2006-11-15
AP 4.5.13 | UEP | Complete draft of D5.4 | 2006-11-30
Action | Responsible | Description | Date | Status
AP.4.8.1 | EURECOM, ALL | Partners have to complete the indicators for D8.1 | 2006-10-31
AP.4.8.2 | EURECOM & DCU | collate & check the completed indicators | 2006-11-20
AP.4.8.3 | QMUL | Craig to check with the PO concerning the structure of the pre-review and the various deadlines for submission. | 2006-09-15
AP.4.8.4 | QMUL | Craig to check with the PO concerning the structure of the review and the various deadlines for submission. | 2006-09-15
AP.4.8.5 | QMUL | Craig discuss with the PO and to decide the content of the pre-review & review, and distribute the work amongst the project partners | 2006-10-14
AP.4.8.6 | QMUL | Craig to inform partners of the various WP1 Deliverables due for M12, eg Audits, and financial plan | 2006-11-27
AP.4.8.7 | DCU | ensure that they have access to all required information and materials for the report on integration activities | 2006-10-14
AP.4.8.8 | DCU | distribute a draft report for D8.3 amongst partners for comments | 2006-11-27
AP.4.8.9 | ALL | report comments on D8.3 back to DCU | 2006-12-11
Nr. | Responsible | Description | Date | Status
Music Video Indexing
AP4.3.1 | DCU | Send action plan for ‘Music Video Indexing’ to WP3 for commenting/joining | 2006-08-30 | Done
AP4.3.2 | GET | Build a DVD of additional AV drum sequences and send it to DCU (GET) | 2006-09-01
AP4.3.3 | GET | Set-up an improved drum transcription system trained on drum sequences | 2006-09-27
AP4.3.4 | DCU | Initial version of the automatic segmentation of drum tops | 2006-09-15
AP4.3.5 | GET | Build an audiovisual drum transcription system based on output of both algorithms on drum only signals and on drum + other musicians signals | 2006-10-31
AP4.3.6 | DCU | Build a drum stick tracking ground-truth to evaluate the potential of the visual information on this task | 2006-10-01
AP4.3.7 | DCU/GET | Feasibility/Usefulness study for an automatic drum stick tracking algorithm | 2006-10-15
AP4.3.8 | DCU/GET | · If feasible: Build an audiovisual drum transcription system using high-level video features | No date
· If feasible: Comparison between the two approaches “low-level video/audio transcription” and “high-level video/audio transcription”
AP4.3.9 | INA/GET | Investigation on access to talk-show like TV programs | 2006-10-01
AP4.3.10 | GET | Send the current music video database to DCU | 2006-09-01
AP4.3.11 | GET/DCU | Specification of the task (ideal database, genres definition feasibility study, resource needed) | 2006-10-01
AP4.3.12 | GET/DCU | Decision to continue or stop | 2006-10-15
Temp. alignment between audio and complementary text for classical plays
AP4.3.13 | GET | Specification / Development of automatic alignment tool | 2006-10-30
AP4.3.14 | INA | Segmentation of a larger subset of recordings | 2006-11-30
AP4.3.15 | GET | Per verse, half-verse syllable, phone computation of prosodic marks (F0, energy, duration) | 2007-01-30
AP4.3.16 | INA | Specification / Development of a visualisation / Search tool | 2007-04-30
AP4.3.17 | GET | Statistical analysis of prosodic features | 2007-04-30
Proposal: Study on audio classif. robust against sound deformations
AP4.3.18 | GET | Action plan setup with TUB and QMUL, to be sent to WP3 for commenting/joining | 2006-09-15
Sparse representation for audio indexing
AP4.3.19 | GET | Submit paper to IEEE Trans. on SALP | 2006-09-15
AP4.3.20 | GET | Specification on putting up ground truth data in order to get transcription of midi/wav | 2006-10-30
AP4.3.21 | GET/TUB | discussion on how to integrate TUB into collaboration ‘Sparse representation for audio indexing’ | 2006-09-15
D3.3 Techn. Report on Audio and Speech Proc.
AP4.3.22 | GET | TOC | 2006-09-20
AP4.3.23 | QMUL, TUB, DFKI, DCU, GET | Partner contributions of sections/chapters | 2006-10-31
AP4.3.24 | GET | Consolidated version 15 Nov. 2006 | 2006-11-15
AP4.3.25 | ? | Proof reading: | 2006-11-30
AP4.3.26 | GET | Final version | 2006-12-15
Proposal: On audiovisual indexing (Segment a TV feed to programs)
AP4.3.27 | GET | Action plan setup (corpus identification, expected partner contributions) with INA, DCU, TUB and QMUL; to be sent to WP3 for commenting/joining | 2006-08-31
Proposal: Study on audio classif. robust against sound deformations
AP4.3.28 | GET | Action plan setup with TUB and QMUL; to be sent to WP3 for commenting/joining | 2006-09-15
Video region segmentation tool
AP4.3.29 | EURECOM | Integration of ncuts algorithm into segmentation tool | 2006-09-30
AP4.3.30 | ITI | check if the integration of saliency algorithm into segmentation tool is feasible | 2006-09-15
AP4.3.31 | DCU | integration of semi-automatic object based segmentation tool including tracking functionality | 2006-10-31
AP4.3.32 | EPFL | Development of a software tool for the evaluation of segmentation algorithms (evaluation metrics) | 2006-10-31
AP4.3.33 | ITI | send list of WP4 requirements on low level feature description to DCU/JRS | 2006-09-15
AP4.3.34 | DCU/JRS | Specify requirements for MPEG‑7 description (segmentation tool output format) | 2006-09-30
AP4.3.35 | JRS | Specify MPEG‑7 descriptors (segmentation tool output format) | 2006-10-15
AP4.3.36 | DCU | Implementation of MPEG-7 descriptors (segmentation tool output format) | 2006-11-15
Ground truth setup of video/image region segmentation
AP4.3.37 | QMUL | set up of ground truth for video/image region segmentation (starts with availability of the video region segmentation tool) | 2006-11-30
D3.2 Technical Report on Moving Object Segmentation
AP4.3.38 | DCU | Setup of D3.2, input from DCU, JRS, ITI, EURECOM and EPFL, for a detailed roadmap see section 2.2.3. | 2006-12-01
Improve speech2text by using ontologies
AP4.3.39 | GET | Continuously update on getting evaluation data set for ‘improve speech2text by using ontologies’ | ongoing
AP4.3.40 | GET | Study feasibility of using news data from INA as evaluation data set | 2006-09-30
AV content description
AP4.3.41 | All | Continuously: Whenever MPEG-7 metadata exchange is required by any collaboration within KS update MPEG-7 description requirements document on document store and notify JRS for specification. | ongoing
AP4.3.42 | TUB, GU, GET, INA, EURECOM, EPFL, ITI, KU | Each partner to clarify contribution to WP3.4. Send proposal to JRS and QMUL. | 2006-09-20
AP4.3.43 | JRS | Set-up document with requirements and ideas on MPEG-7 description infrastructure | 2006-09-15
AP4.3.44 | TUB, GU, GET, INA, EURECOM, EPFL, ITI, KU, CWI | Send your planned contributions / feedback/ideas on MPEG‑7 infrastructure requirements document to JRS | 2006-09-30
Number | Partners | Description | Deadline | status
AP4.4.1 | KU, UEP | Write a detailed description of the design patterns and their usage (part of D4.1) | 2006-09-15
AP4.4.2 | JRS, KU, ITI, CWI | Determine which MPEG-7 descriptors are needed for the annotation tool prototypes | 2006-09-15
AP4.4.3 | UEP | Use the design patterns of the multimedia ontology to implement the descriptors from AP2 in an OWL ontology | 2006-10-15
Create a Protégé project and submit it to the K-Space SVN repository
Implement the design patterns based on the DOLCE OWL code
Implement the descriptors
AP4.4.4 | UEP, DFKI | Ensure that the example domain ontology which was provided by DFKI can be used in combination with the OWL multimedia ontology to annotate the example images | 2006-10-15
Integrate the domain ontology in the multimedia ontology SVN repository
Add some example annotations to the SVN repository that demonstrate how the annotation is carried out (part of D4.1)
AP4.4.5 | ITI, KU | Implement the M-OntoMat Annotizer 2.0 plugin for OntoMat 0.82 according to the architecture draft. First prototype of M-OntoMat Annotizer 2.0 has to provide | 2006-12-22
Semantic annotation of image segments according to the new multimedia ontology infrastructure
Export to RDF (and probably storage in the new WP5 metadata store)
AP4.4.6 | KU, ITI, JRS, CWI | Describe the architecture of the tools and their functionalities (part of D4.1)
AP4.4.7 | ITI, QMUL | Finalise classifier interface | 2006-09-15
AP4.4.8 | EURECOM, ITI | Fusion of Classifiers for MS4.2/D4.2 | 2006-10-01
AP4.4.9 | EPFL, ITI | Decide on the Role of Context for MS4.2/D4.2 | 2006-09-15
AP4.4.10 | ITI, DFKI | Decide on the role of information from text for KAA along with a suitable scenario | 2006-10-01
AP4.4.11 | KU, ITI | Finalise the interface of the KAA system of WP4.2 with the Ontology Infrastructure of WP4.1 | 2006-10-01
AP4.4.12 | ITI, all | Finalise D4.2 ToC | 2006-10-01
AP4.4.13 | KU | Decide on whether constraint reasoning will be employed in MS4.3 | 2006-09-15
AP4.4.14 | EPFL, EURECOM | Define contribution in MS4.3 | 2006-09-15
AP4.4.15 | ITI, all | Finalise D4.3 ToC | 2006-10-01
AP4.4.16 | ITI UEP | ITI send more examples to UEP for the rule-based reasoning | 2006-09-30
AP4.4.17 | ITI | ITI provide report for the survey of existing reasoners | 2006-10-31
AP4.4.18 | GU | Initial draft of mining application | 2006-10-15
Partner feedback
AP4.4.19 | GU | Partner feedback | 2006-10-31
AP4.4.20 | QMUL | To integrate intelligent image classification techniques into the multimodal analysis framework | 2006-09-06
AP4.4.21 | QMUL | To add functionalities into the multimodal analysis framework | 2006-10-31
AP4.4.22 | QMUL | To deliver the final version of the multimodal analysis framework for the pre-review meeting | 2006-11-30
AP4.4.23 | QMUL | Table of contents for D4.5 sent to the partners | 2006-09-15
AP4.4.24 | QMUL, DCU, CWI, GET, GU | Initial contribution to D4.5 | 2006-11-15
AP4.4.25 | QMUL | First draft of D4.5 available for feedback | 2006-12-01
AP4.4.26 | QMUL | Final version of D4.5 delivered | 2006-12-20

## Sheet2
Action | Responsible | Description | Date | Status
AP4.3.1 | DCU | Send action plan for ‘Music Video Indexing’ to WP3 for commenting/joining | 2006-08-30 | Done
AP4.3.27 | GET | Action plan setup (corpus identification, expected partner contributions) with INA, DCU, TUB and QMUL; to be sent to WP3 for commenting/joining | 2006-08-31
AP4.3.10 | GET | Send the current music video database to DCU | 2006-09-01
AP4.3.2 | GET | Build a DVD of additional AV drum sequences and send it to DCU (GET) | 2006-09-01
AP4.5.4 | KU | Create architecture draft | 2006-09-01 | done
AP4.4.20 | QMUL | To integrate intelligent image classification techniques into the multimodal analysis framework | 2006-09-06
AP4.6.3 | DCU | Distribute the plan for gathering of all resources which are ready to be contributed | 2006-09-08
AP4.7.4 | QMUL | Add to the bi-monthly report a mandatory field for news for every partners | 2006-09-10
AP4.2.2 | QMUL | to set up a webpage reflecting the status of the exchanges. Basis will be the Excel sheet, amended by the intended exchanges mentioned above | 2006-09-15
AP4.2.8 | GET | identify responsible persons from each university partner | 2006-09-15
AP4.2.9 | GET | define a list of modules based on pre-existing master programs related to K-Space | 2006-09-15
AP4.3.18 | GET | Action plan setup with TUB and QMUL, to be sent to WP3 for commenting/joining | 2006-09-15
AP4.3.19 | GET | Submit paper to IEEE Trans. on SALP | 2006-09-15
AP4.3.21 | GET/TUB | discussion on how to integrate TUB into collaboration ‘Sparse representation for audio indexing’ | 2006-09-15
AP4.3.28 | GET | Action plan setup with TUB and QMUL; to be sent to WP3 for commenting/joining | 2006-09-15
AP4.3.30 | ITI | check if the integration of saliency algorithm into segmentation tool is feasible | 2006-09-15
AP4.3.33 | ITI | send list of WP4 requirements on low level feature description to DCU/JRS | 2006-09-15
AP4.3.4 | DCU | Initial version of the automatic segmentation of drum tops | 2006-09-15
AP4.3.43 | JRS | Set-up document with requirements and ideas on MPEG-7 description infrastructure | 2006-09-15
AP4.4.1 | KU, UEP | Write a detailed description of the design patterns and their usage (part of D4.1) | 2006-09-15
AP4.4.13 | KU | Decide on whether constraint reasoning will be employed in MS4.3 | 2006-09-15
AP4.4.14 | EPFL, EURECOM | Define contribution in MS4.3 | 2006-09-15
AP4.4.2 | JRS, KU, ITI, CWI | Determine which MPEG-7 descriptors are needed for the annotation tool prototypes | 2006-09-15
AP4.4.23 | QMUL | Table of contents for D4.5 sent to the partners | 2006-09-15
AP4.4.7 | ITI, QMUL | Finalise classifier interface | 2006-09-15
AP4.4.9 | EPFL, ITI | Decide on the Role of Context for MS4.2/D4.2 | 2006-09-15
AP4.6.5 | QMUL, DCU, TUB | Propose/discuss the plan for making the access to the three SVN repositories transparent | 2006-09-15
AP4.8.3 | QMUL | Craig to check with the PO concerning the structure of the pre-review and the various deadlines for submission. | 2006-09-15
AP4.8.4 | QMUL | Craig to check with the PO concerning the structure of the review and the various deadlines for submission. | 2006-09-15
AP4.3.22 | GET | TOC | 2006-09-20
AP4.3.42 | TUB, GU, GET, INA, EURECOM, EPFL, ITI, KU | Each partner to clarify contribution to WP3.4. Send proposal to JRS and QMUL. | 2006-09-20
AP4.3.3 | GET | Set-up an improved drum transcription system trained on drum sequences | 2006-09-27
AP4.2.3 | ALL | all partners submit potential candidates to QMUL; skills and references to be described in more detail! Pool will be based on the PhD exchange details | 2006-09-30
AP4.2.4 | ALL | from September onwards / partners to contact actively spin-off and partner companies with the existing list | 2006-09-30
AP4.2.5 | TUB | provide an information document on shared teaching resources (list of contacts, objectives) | 2006-09-30
AP4.2.7 | GU, EURECOM | provide details of the intended teaching resource submissions to TUB | 2006-09-30
AP4.3.29 | EURECOM | Integration of ncuts algorithm into segmentation tool | 2006-09-30
AP4.3.34 | DCU/JRS | Specify requirements for MPEG‑7 description (segmentation tool output format) | 2006-09-30
AP4.3.40 | GET | Study feasibility of using news data from INA as evaluation data set | 2006-09-30
AP4.3.44 | TUB, GU, GET, INA, EURECOM, EPFL, ITI, KU, CWI | Send your planned contributions / feedback/ideas on MPEG‑7 infrastructure requirements document to JRS | 2006-09-30
AP4.4.16 | ITI UEP | ITI send more examples to UEP for the rule-based reasoning | 2006-09-30
AP4.5.10 | QMUL, KU, JRS, ITI | Suggest contribution to task 5.4 | 2006-09-30
AP4.5.2 | ITI, KU | to describe how FuzzyOWL can be stored in existing RDF repositories | 2006-09-30
AP4.5.7 | CWI | finalize TOC of D5.3 | 2006-09-30
AP4.6.1 | GU | Fill questionnaires on planned contribution | 2006-09-30
AP4.6.2 | EURECOM | Finalize the status on the existing tools and planned tools and to report to DCU | 2006-09-30
AP4.6.6 | QMUL, DCU, TUB | Implementation of the single access point to all three SVN repositories and a common framework for login | 2006-09-30
AP4.7.1 | QMUL | Add some internal deliverables to the web page | 2006-09-30
AP4.7.14 | UEP, ALL | TOC of next newsletter | 2006-09-30
AP4.7.17 | EPFL, ALL | Generate a candidate TOC of the (first) book. End of September | 2006-09-30
AP4.7.18 | ALL, EPFL | Contact MPEG (EPFL?) to manage a liaison activity on the semantic multimedia | 2006-09-30
AP4.7.19 | CERTH, ALL | Finalize the list representative of each partner of K-Space for W3C | 2006-09-30
AP4.7.2 | QMUL | Add PR material | 2006-09-30
AP4.7.3 | QMUL | Action on the participation of K-Space Webpage to the IST Award for best web pages. | 2006-09-30
AP4.7.5 | QMUL | Add a link to SmaRT cluster web page | 2006-09-30
AP4.7.6 | QMUL | Add the W3C logo | 2006-09-30
AP4.3.11 | GET/DCU | Specification of the task (ideal database, genres definition feasibility study, resource needed) | 2006-10-01
AP4.3.6 | DCU | Build a drum stick tracking ground-truth to evaluate the potential of the visual information on this task | 2006-10-01
AP4.3.9 | INA/GET | Investigation on access to talk-show like TV programs | 2006-10-01
AP4.4.10 | ITI, DFKI | Decide on the role of information from text for KAA along with a suitable scenario | 2006-10-01
AP4.4.11 | KU, ITI | Finalise the interface of the KAA system of WP4.2 with the Ontology Infrastructure of WP4.1 | 2006-10-01
AP4.4.12 | ITI, all | Finalise D4.2 ToC | 2006-10-01
AP4.4.15 | ITI, all | Finalise D4.3 ToC | 2006-10-01
AP4.4.8 | EURECOM, ITI | Fusion of Classifiers for MS4.2/D4.2 | 2006-10-01
AP4.6.4 | DCU, ALL | Gather resources in the repository. This will include collection of tools which do not have already their own official web-page and which are ready | 2006-10-02
AP4.7.12 | CWI | CWI offers to create the SmaRT webpage | 2006-10-08
AP4.8.5 | QMUL | Craig discuss with the PO and to decide the content of the pre-review & review, and distribute the work amongst the project partners | 2006-10-14
AP4.8.7 | DCU | ensure that they have access to all required information and materials for the report on integration activities | 2006-10-14
AP4.3.12 | GET/DCU | Decision to continue or stop | 2006-10-15
AP4.3.35 | JRS | Specify MPEG‑7 descriptors (segmentation tool output format) | 2006-10-15
AP4.3.7 | DCU/GET | Feasibility/Usefulness study for an automatic drum stick tracking algorithm | 2006-10-15
AP4.4.18 | GU | Initial draft of mining application. Partner feedback. | 2006-10-15
AP4.4.3 | UEP | Use the design patterns of the multimedia ontology to implement the descriptors from AP2 in an OWL ontology. Create a Protégé project and submit it to the K-Space SVN repository. Implement the design patterns based on the DOLCE OWL code. Implement the descriptors | 2006-10-15
AP4.4.4 | UEP, DFKI | Ensure that the example domain ontology which was provided by DFKI can be used in combination with the OWL multimedia ontology to annotate the example images. Integrate the domain ontology in the multimedia ontology SVN repository. Add some example annotations to the SVN repository that demonstrate how the annotation is carried out (part of D4.1) | 2006-10-15
AP4.5.3 | CWI | To provide outline and to decide on whether to include chapter 4 in D5.1 | 2006-10-15
AP4.5.5 | All | Provide specifications for components of the metadata store | 2006-10-15
AP4.2.10 | GET | inform participants about the meeting or lack of it | 2006-10-30
AP4.2.6 | TUB | open up website for accessing resources | 2006-10-30
AP4.3.13 | GET | Specification / Development of automatic alignment tool | 2006-10-30
AP4.3.20 | GET | Specification on putting up ground truth data in order to get transcription of midi/wav | 2006-10-30
AP4.5.11 | DFKI, UEP; DCU, GU | First experiments in text-video mapping in the football domain | 2006-10-30
AP4.3.23 | QMUL, TUB, DFKI, DCU, GET | Partner contributions of sections/chapters | 2006-10-31
AP4.3.31 | DCU | integration of semi-automatic object based segmentation tool including tracking functionality | 2006-10-31
AP4.3.32 | EPFL | Development of a software tool for the evaluation of segmentation algorithms (evaluation metrics) | 2006-10-31
AP4.3.5 | GET | Build an audiovisual drum transcription system based on output of both algorithms on drum only signals and on drum + other musicians signals | 2006-10-31
AP4.4.17 | ITI | ITI provide report for the survey of existing reasoners | 2006-10-31
AP4.4.19 | GU | Partner feedback | 2006-10-31
AP4.4.21 | QMUL | To add functionalities into the multimodal analysis framework | 2006-10-31
AP4.5.6 | KU | deliver D5.2 | 2006-10-31
AP4.7.13 | UEP, ALL | Offline discussion on the brochure. | 2006-10-31
AP4.7.16 | DFKI | To provide for an updated document on the Scientific Forum, which will be the base for the final choice of the legal form of the Scientific Forum | 2006-10-31
AP4.7.21 | ALL | DFKI and GET to provide for an example of a past submission (End of October) | 2006-10-31
AP4.8.1 | EURECOM, ALL | Partners have to complete the indicators for D8.1 | 2006-10-31
AP4.8.1 | EURECOM, ALL | Partners have to complete the indicators for D8.1 | 2006-10-31
AP4.3.24 | GET | Consolidated version 15 Nov. 2006 | 2006-11-15
AP4.3.36 | DCU | Implementation of MPEG-7 descriptors (segmentation tool output format) | 2006-11-15
AP4.4.24 | QMUL, DCU, CWI, GET, GU | Initial contribution to D4.5 | 2006-11-15
AP4.5.12 | UEP | Partial draft of D5.4 | 2006-11-15
AP4.5.8 | ALL | D5.3 provide chapters | 2006-11-15
AP4.8.2 | EURECOM & DCU | collate & check the completed indicators | 2006-11-20
AP4.8.6 | QMUL | Craig to inform partners of the various WP1 Deliverables due for M12, eg Audits, and financial plan | 2006-11-27
AP4.8.8 | DCU | distribute a draft report for D8.3 amongst partners for comments | 2006-11-27
AP4.3.14 | INA | Segmentation of a larger subset of recordings | 2006-11-30
AP4.3.25 | ALL | Proof reading: | 2006-11-30
AP4.3.37 | QMUL | set up of ground truth for video/image region segmentation (starts with availability of the video region segmentation tool) | 2006-11-30
AP4.4.22 | QMUL | To deliver the final version of the multimodal analysis framework for the pre-review meeting | 2006-11-30
AP4.5.13 | UEP | Complete draft of D5.4 | 2006-11-30
AP4.5.9 | CWI | first complete draft of D5.3 | 2006-11-30
AP4.3.38 | DCU | Setup of D3.2, input from DCU, JRS, ITI, EURECOM and EPFL, for a detailed roadmap see section 2.2.3. | 2006-12-01
AP4.4.25 | QMUL | First draft of D4.5 available for feedback | 2006-12-01
AP4.8.9 | ALL | report comments on D8.3 back to DCU | 2006-12-11
AP4.3.26 | GET | Final version | 2006-12-15
AP4.5.1 | JRS, ITI, KU | decide which datatypes to support | 2006-12-15
AP4.4.26 | QMUL | Final version of D4.5 delivered | 2006-12-20
AP4.4.5 | ITI, KU | Implement the M-OntoMat Annotizer 2.0 plugin for OntoMat 0.82 according to the architecture draft. First prototype of M-OntoMat Annotizer 2.0 has to provide. Semantic annotation of image segments according to the new multimedia ontology infrastructure. Export to RDF (and probably storage in the new WP5 metadata store) | 2006-12-22
AP4.3.15 | GET | Per verse, half-verse syllable, phone computation of prosodic marks (F0, energy, duration) | 2007-01-30
AP4.3.16 | INA | Specification / Development of a visualisation / Search tool | 2007-04-30
AP4.3.17 | GET | Statistical analysis of prosodic features | 2007-04-30
AP4.7.15 | UEP, ALL | Draft of next newsletter | 2006-11-31
AP4.3.8 | DCU/GET | If feasible: Build an audiovisual drum transcription system using high-level video features. Also a comparison between the two approaches “low-level video/audio transcription” and “high-level video/audio transcription” | 2006-30-11
AP4.2.1 | ALL | report all exchanges to GU – not just PhD exchanges | Ongoing
AP4.3.39 | GET | Continuously update on getting evaluation data set for ‘improve speech2text by using ontologies’ | ongoing
AP4.3.41 | All | Continuously: Whenever MPEG-7 metadata exchange is required by any collaboration within KS update MPEG-7 description requirements document on document store and notify JRS for specification. | ongoing
AP4.7.11 | TUB | Link the web page to WP2 teaching resources, once the license issues have been solved | Ongoing
AP4.7.20 | ALL, GET, DFKI | Provide for new technology transfer items to GET (ALL) | Ongoing
AP4.7.7 | QMUL, ALL | Add public deliverables to the webpage | Ongoing
AP4.7.8 | QMUL, ALL | Add publications, together with (a link to) the paper | Ongoing
AP4.7.9 | ALL | Update regularly news sections (including conferences etc) and list of publications. Send to Krishna at QMUL. | Ongoing
AP4.7.10 | DCU | Send to QMUL (links to) downloadable show cases demonstrators (DCU) | When tools are available
AP4.4.6 | KU, ITI, JRS, CWI | Describe the architecture of the tools and their functionalities (part of D4.1)