Title	: WP7 meeting

Date & Time	: 2006-08-28 & 11:50

Date Approved	:

Location	: Joanneum Research, Graz, Austria

Document	: input.doc

Chair	: Thierry Declerck

Author(s)	: Thierry Declerck

Affiliation(s)	: DFKI

Attendees

| Name | Email | Affiliation |
| --- | --- | --- |
| Peter Wilkins | Peter.Wilkins@computing.dcu.ie | DCU |
| Simon Schenk | sschenk@uni-koblenz.de | KU |
| Werner Haas | Werner.haas@joanneum.at | JRS |
| Craig Stewart | craig.stewart@elec.qmul.ac.uk | QMUL |
| Andreas Cobet | cobet@nue.tu-berlin.de | TUB |
| Vassilis Tzouvaras | tzouvaras@image.ntua.gr | CERTH |
| Vojtech Svatech | Svatek@vse.cz | UEP |
| Josef Petrak | jspetrak@gmail.com | UEP |
| Jana Urban | jana@dcs.gla.ac.uk | GU |
| Bernard Merialdo | Bernard.Merialdo@eurecom.fr | EURECOM |
| Thierry Declerck | declerck@dfki.de | DFKI |

- Introduction and Overview

The meeting started on schedule at 11.50 with Thierry Declerck (DFKI) presenting the welcome address, approval of agenda. Thierry Declerck also takes the minutes and formulates on-line the action points for the next months.

Title of the WP: Joint programme of activities to spread excellence

Objectives

- To disseminate the technical developments of the network across the broad research community

- To influence and contribute to related knowledge-based multimedia standardisation activities

- To support technology transfer to industry.

2.0 Main items discussed

WP7.1 Updates of the K-Space webpage: The K-Space Webpage is being continuously updated. Call to the WP7 partners to submit items for actualising the content of the webpage

We discussed if K-Space should participate at the IST Award for best web page? The partners agree to go for it.

Should we provide for localized K-Space webpages? Might be too time intensive. To be discussed at TMC.

We establish a first candidate TOC for the next Newsletter:

  - Headlines: Summer School

  - Interview with PO

  - Interview with either IAB and SAB.

  - Report on actual TRECVid

  - Report on results of the (parts of) the project so far.

  - Report on IST

  - Report on Standardisation activities

  - Report on invited talks etc. (special session, special issues)

  - Job adverts (academic and industrial)

  - Etc.

Newsletter Brochure: What needs to be updated? For example update the images. General issue: All partners to inform UEP about conferences, exhibitions etc., at which K-Space partners can distribute brochures and newsletter (specify the amount). A list is being established. Further suggestion: Have the next newsletter draft versions in month 11, 17, giving enough time for editorial board to react. Next newsletter TOC available in month 9 and 15

WP7.2 Report on State of the SAMT 2006 conference. Very positive development.

WP7.3 Discussion on the Scientific Forum led to a reduction of possible legal forms for the Scientific Forum between “Verein” and “Stichting”. More detailed info on both is needed, in the next version of the WP7.3 document.

WP7.4 Discussion on the state of the state of development for the K-Space book(s) takes place.

WP7.5 Short summary on activities related with exhibitions

WP7.6 Report on standardisation activities. K-Space is member of W3C. K-Space members contribute to the creation of a W3C incubation group and also to ISO standardisation activities. This is very productive item within WP7.

Call for participation to the technology transfer item.

Summary: WP7 is doing well for the time being!

A list of action points for the next period has been established and is displayed below.

2.0 Action Points discussed

AP.4.7.1: (QMUL, ALL) partners have to add some internal deliverables to the web page, date: 2006-09-31

AP.4.7.2: (QMUL, ALL) partners to submit to QMUL PR material to be added to the web page, date: 2006-09-31

AP.4.7.3: (QMUL) QMUL to take action on the participation of K-Space Webpage to the IST Award for best web pages (deadline, 10.9?) date: 2006-09-09

AP.4.7.4: (QMUL) QMUL to add to the bi-monthly report a mandatory field for news, date: 2006-09-10

AP.4.7.5: (QMUL) QMUL to add a link to SmaRT cluster web, date: 2006-09-31

AP.4.7.6: (QMUL) QMUL to add the W3C logo, date: 2006-09-31

AP.4.7.7: (QMUL, ALL) partners to submit to QMUL public deliverables to add to the webpage, date: continously

AP.4.7.8: (QMUL, ALL) Partners to submit to QMUL conferences etc., and list of publications, together with (a link to) the paper (if available) for adding to the Webpage, date: continuously

AP.4.7.9: (QMUL, ALL) Partners to Update regularly news sections, date: continuously.

AP.4.7.10: (DCU, ALL) Partners to send to DCU and QMUL links to downloadable show cases and demonstrators, date: continuously.

AP.4.7.11: (TUB, ALL) Link the web page to WP2 teaching resources, once the license issues have been solved. Report on the state of license, date: 2006-12-04.

AP.4.7.12: (CWI) CWI offers to design the SmaRT web page. Date, 2006-10-08.

AP.4.7.13: (UEP, ALL). Offline Discussion on the Brochure. Results of the discussion to be delivered. Date, 2006-10-31.

AP.4.7.14: (UEP, ALL) UEP to deliver the TOC of the 2nd issue of the newsletter. Date, 2006-09-31.

AP.4.7.15: (UEP, ALL) UEP to deliver the draft of the 2nd issue of the newsletter. Date, 2006-11-30.

AP.4.7.16: (DFKI) To provide for an updated document on the Scientific Forum, which will be the base for the final choice of the legal form of the Scientific Forum. Date, 2006-10-31.

AP.4.7.17: (EPFL, ALL). EPFL to contact all partners for a candidate TOC of the (first) book. Date, 2006-09-30

AP.4.7.18: (EPFL, ALL). EPFL to contact MPEG to manage a liaison activity on the semantic multimedia. Date, 2006-09-30.

AP.4.7.19: (CERTH, ALL) CERTH to Finalize the list representative of each partner of K-Space for W3C. Date, 2006-09-30.

AP.4.7.20: (ALL) Provide for new technology transfer items to GET. Date, 2 weeks before each TMC meeting

AP.4.7.21: (GET, DFKI, ALL) DFKI and GET to provide for an example of a past submission. Date, 2006-10-31.

- Summary of Action Points

| Action | Partner Responsible | Description | Date | Status |
| --- | --- | --- | --- | --- |
| AP4.7.1 | QMUL | Add some internal deliverables to the web page | 2006-09-30 |  |
| AP4.7.2 | QMUL | Add PR material | 2006-09-30 |  |
| AP4.7.3 | QMUL | Action on the participation of K-Space Webpage to the IST Award for best web pages. | 2006-09-30 |  |
| AP4.7.4 | QMUL | Add to the bi-monthly report a mandatory field for news for every partners | 2006-09-10 |  |
| AP4.7.5 | QMUL | Add a link to SmaRT cluster web page | 2006-09-30 |  |
| AP4.7.6 | QMUL | Add the W3C logo | 2006-09-30 |  |
| AP4.7.7 | QMUL, ALL | Add public deliverables to the webpage | 2006-08-31 Ongoing |  |
| AP4.7.8 | QMUL, ALL | Add publications, together with (a link to) the paper | 2006-08-31 Ongoing |  |
| AP4.7.9 | ALL | Update regularly news sections (including conferences etc) and list of publications. Send to Krishna at QMUL. | 2006-08-31 Ongoing |  |
| AP4.7.10 | DCU | Send to QMUL (links to) downloadable show cases demonstrators (DCU) | When tools are available |  |
| AP4.7.11 | TUB | Link the web page to WP2 teaching resources, once the license issues have been solved | No fixed date |  |
| AP4.7.12 | CWI | CWI offers to create the SmaRT webpage | 2006-10-08 |  |
| AP4.7.13 | UEP, ALL | Offline discussion on the brochure. | 2006-10-31 |  |
| AP4.7.14 | UEP, ALL | TOC of next newsletter | 2006-09-30 |  |
| AP4.7.15 | UEP, ALL | Draft of next newsletter | 2006-11-31 |  |

| Action | Partner Responsible | Description | Date | Status |
| --- | --- | --- | --- | --- |
| AP4.7.16 | DFKI | To provide for an updated document on the Scientific Forum, which will be the base for the final choice of the legal form of the Scientific Forum | 2006-10-31 |  |
| AP4.7.17 | EPFL, ALL | Generate a candidate TOC of the (first) book. End of September | 2006-09-30 |  |
| AP4.7.18 | ALL, EPFL | Contact MPEG (EPFL?) to manage a liaison activity on the semantic multimedia | 2006-09-30 |  |
| AP4.7.19 | CERTH, ALL | Finalize the list representative of each partner of K-Space for W3C | 2006-09-30 |  |
| AP4.7.20 | ALL, GET, DFKI | Provide for new technology transfer items to GET (ALL) | Ongoing |  |
| AP4.7.21 | ALL | DFKI and GET to provide for an example of a past submission (End of October) | 2006-10-31 |  |