## Sheet1
Activity | QMUL | KU | JRS | ITI | DCU | CWI | GET | INA | EURECOM | GU | DFKI | TUB | EPFL | UEP | Total participants
TOTAL Including Coordination | 169 | 100 | 76 | 91 | 123 | 80 | 105 | 50 | 105 | 96 | 50 | 79 | 89 | 104 | 1317
Integrating activities | 7 | 7 | 5 | 5 | 7 | 7 | 9 | 5 | 7 | 7 | 5 | 8 | 7 | 9 | 95
WP2.1 Exchange of Research Personnel and PhD | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 28
WP2.2 Industrial Placement of Research Personnel | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 15
WP2.3 Shared Teaching Resources | 2 | 2 |  |  | 2 | 2 | 3 |  | 2 | 2 | 1 | 2 | 2 | 3 | 23
WP2.4 Summer School and EU MS and PhD | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 29
Joint research programme | 78 | 81 | 58 | 73 | 102 | 61 | 85 | 35 | 85 | 77 | 33 | 60 | 69 | 75 | 972
WP3.1 Content Structuring | 8 |  | 12 |  | 12 |  | 11 | 10 | 6 | 10 |  |  |  |  | 69
WP3.2 Moving 2D and 3D Object segmentation and indexing | 8 |  | 8 |  | 12 |  | 12 |  | 20 |  |  | 5 | 24 |  | 89
WP3.3 Audio/Speech processing and Text analysis | 2 | [5 empty] | 36 |  |  |  | 10 | 32 |  |  | 80
WP3.4 Content Description |  | 4 | 9 | 4 |  |  | 10 | 10 | 10 | 12 |  | 17 | 10 |  | 86
WP4.1 Specification of a Multimedia Ontology Infrastructure |  | 12 |  | 12 |  | 12 |  |  |  |  | 6 |  |  | 18 | 60
WP4.2 Knowledge assisted MM analysis |  | 6 |  | 16 | 6 |  |  |  | 18 |  |  |  | 24 |  | 70
WP4.3 Multimedia Reasoning and Annotation |  | 6 |  | 19 |  |  |  | 6 | 12 |  | 5 |  | 5 |  | 53
WP4.4 Content-Based MM Mining | 8 |  | 6 |  | 12 | 5 | 6 |  | 14 | 30 |  |  |  |  | 81
WP4.5 Intelligent User Relevance Feedback | 24 |  |  |  | 12 | 8 | 6 |  |  | 12 |  |  |  |  | 62
WP5.1 Knowledge Representation for Multimedia |  | 11 | 6 | 10 |  | 8 | [7 empty] | 15 | 50
WP5.2 Reference Framework for Distributed Semantic Management of Multimedia Metadata |  | 23 |  | 4 |  | 8 | [7 empty] | 16 | 51
WP5.3 Semantics-based Interaction with Multimedia | 12 | 6 | 4 | 4 | 12 | 18 |  | 7 |  | 7 |  |  |  |  | 70
WP5.4 Knowledge Extraction from Complementary Sources | 12 | 6 | 6 | [7 empty] | 8 |  |  | 19 | 51
WP6.1 Distributed Research Environment Design | 2 | 5 | 5 | 2 | 30 | 1 | 2 | 1 | 3 | 4 | 2 | 4 | 4 | 5 | 70
WP6.2 Research Resource Sharing | 2 | 2 | 2 | 2 | 6 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 30
Spreading of excellence activities | 11 | 10 | 11 | 11 | 9 | 10 | 9 | 8 | 9 | 9 | 10 | 9 | 11 | 18 | 145
WP7.1 Website, Newsletter, K-Space Posters and Brochures | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 9 | 26
WP7.2 K-Space Conference - The European Workshop on the Integration of Knowledge, Semantics and Digital Media Technology (EWIMT) | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 30
WP7.3 Towards a Scientific Forum in Multimedia Knowledge Extraction and Analysis | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 1 | 2 | 2 | 29
WP7.4 Joint Publications | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 26
WP7.5 Exhibitions and Demonstrations | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 17
WP7.6 Contribution to Standards and Technology Transfer | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 17
Assessment and Evaluation | 3.9 | 1.1 | 1.3 | 1.1 | 4.1 | 1.3 | 1.3 | 1.3 | 3.3 | 2.1 | 1.3 | 1.3 | 1.3 | 1.3 | 26
WP8.1 Definition of Project Objective Tree and Project Assessment Metrics | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 2.6
WP8.2 Annual Project Review and Project Re-Orientation | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 17
WP8.3 Monitoring and Evaluation of Integration Activities | 0.8 |  | 0.2 |  | 3 | 0.2 | 0.2 | 0.2 |  | 1 | 0.2 | 0.2 | 0.2 | 0.2 | 6.4
Consortium management activities | 69.1 | 0.9 | 0.7 | 0.9 | 0.9 | 0.7 | 0.7 | 0.7 | 0.7 | 0.9 | 0.7 | 0.7 | 0.7 | 0.7 | 79
WP1.3 Planning and Coordination of Project and Meetings | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP1.2 Communication With the EU Commission | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
WP1.4 Financial Planning | 6 | 0.2 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 6.8
WP1.5 Accounting and Financial Audits | 9 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 11.6
WP1.6 Handling of Legal and Ethical Matters | 3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 4.3
WP1.7 Concertation, Consensus and Clusters | 9 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 11.6
WP1.1 Overall Coordination of the Joint Activities of the Network | 27.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.1
WP1.8 Annual coordination and writing of Annex 1 | 6 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 8.6
Note on O9: uros damnanovic: should be 75